## Sheet1
Sprintable Stories | Tasks |  |  | Definition of Done
As the Product Owner I want the code for GutenSearch to be unit-tested. We must have unit tests that cover 100% of the methods and statements and 80% of the branches that are not part of the GUI. | Start by testing code that works (i.e. Index.java), since it should keep working even after edits. (10 Hours) (Done by: Rebecca Andrews) |  |  | All tests have been created, for all classes, methods, and branches.
As the Product Owner I want the code for GutenSearch to be system-tested. We must have written documents that describe the step-by-step tests that will be performed, those tests must cover all GUI elements, and there must be a checklist that demonstrates that the tests have been conducted and the failures (and symptoms of those failures) that occurred. | Go through each user route through the program. And document each expected result and procedure. (5 Hours) (Done by: Thompson Schiefelbein) | Go through each admin route through the program. And document each expected result and procedure. (5 Hours) (Done by: Thompson Schiefelbein) | Due to some difficulties, Thompson has requested an extension. | When two documents have been created, one for actions a user /admin can make, and another for unit testing.
As the Product Owner I want the product to be more usable. (User testing of the current increment indicates that GutenSearch is not usable and falls far short of related products like Copernic, DocFetcher, and Agent Ransack. ) | Edit GUI, to make it more user-friendly, and appealing. (i.e. one Frame, no pop-ups, implement Menu Bar more (remove Buttons). (8 Hours) (Done by: Affan Sheikh & John Unger) | Research what color theme is being used by major programs. (1 Hours) (Done by: John Unger & Affan Sheikh) | split programs (to admin, and to user) (implement Formatter/ Style Guide). (3 Hours) (Done by: Affan Sheikh) | 2 different programs (user and admin), that run together, and look appealing.
As an Administrator, I want to be able to specify multiple files for indexing at the same time. | Research how to go through multiple files at the same time (i.e. one right after the other). (1 Hour) (Done by: Derek Hardy) | Implement the ability to select multiple files, and index multiple files. (4 Hours) (Done by: John Unger & Derek Hardy) |  | Have the abiltiy to select multiple files and have it be indexed.
As an Administrator, I want to be able to specify that an entire directory should be indexed. | Implement a function on the GUI to have ability to select just a folder, or specific files. (2 Hours) (Done by: Derek Hardy) | Alter index.java to go through multiple files. (2 Hour) --It was not Index.java that was edited-- (Done by: John Unger) |  | Have the abiltiy to select a directory and have it be indexed.
---------------------------------------------------------------------------------------- These are the epics: ----------------------------------------------------------------------------------------
As an Administrator, I want to be able to see the progress of an ongoing indexing operation. | This has been requested to be an epic.
As an Administrator, I want to be able to cancel an an ongoing indexing operation. | This has been requested to be an epic.
As an Administrator, I want to be able to merge multiple indexes.
As a User, I want to be able to see a history of search results (for searches performed during this "session").
As a User, I want to be able to save a history of search results to a file.
As a User, I want to be able to retrieve a saved history of search results from a file.
What needs to be Submitted
The following must be submitted at the end of the Sprint using Canvas.
A file named unit-testing.pdf containing the results of the last set of unit tests that were run. This report may be nothing more than a collection of "screenshots" of EclEmma reports.
A file named system-testing.pdf containing the results of the last set of system tests that were run. This report must contain a description of the testing protocol that was used, the failures that were identified (if any), and the symptoms of those failures.
A file named source.zip containing all of the source code (and nothing else), including code that was used for testing. The organization of source.zip must correspond to the packaging scheme being used.
A file named documentation.zip containing all of the .html files and other associated files generated by javadoc.
A file named texts.zip containing the source documents that you are using for demonstrations.
One or more executable .jar files that can be used to run GutenSearch. The .jar files must "stand alone" (other than the source documents they require as input). In other words, it must be possible for a user to download the .jar files and execute them from the operating system without doing anything else.
A spreadsheet containing the status of all Sprint Backlog Items and tasks at the end of the Sprint.